## RiskTable
Risk Assessment Template | [10 empty] | #VALUE!
| Last Updated: | 2024-10-24 | [8 empty] | Risk Assessment Template
© 2024 Vertex42 LLC
ACTION ITEMS
# | Failure Mode | CAUSE of Failure | LIKELIHOOD | EFFECT of Failure | IMPACT | RISK SCORE | Recommended Actions | Action Owner | Action Due Date | % Complete | Notes
1 | Motor overheating | Overuse or poor ventilation | 2 | Motor failure, bike stops functioning | 4 | 8 | Improve ventilation design and use heat-resistant materials | Design Engineer | 2024-10-20 | 50% | Some Notes about this item
2 | Battery overcharge | Faulty charging system | 2 | Battery explosion or failure | 5 | 10 | Implement advanced battery management system | Battery Engineer | 2024-10-15 | 100%
3 | Brake pad wear | Normal wear and tear | 5 | Reduced stopping ability, increased stopping distance | 4 | 20 | Add wear indicators on brake pads | Maintenance Team | 2024-11-01
4 | Frame crack | Poor material quality or stress points | 2 | Structural failure, rider injury | 5 | 10 | Use stronger, lighter materials and stress-testing | Materials Engineer | 2024-11-10 | 30%
5 | Low battery capacity | Poor battery quality or aging | 4 | Shorter ride distance | 3 | 12 | Improve battery quality control and user notifications | Battery Engineer | 2024-10-25
6 | Display malfunction | Faulty wiring or water ingress | 3 | Loss of speed and battery status information | 2 | 6 | Improve waterproofing and use higher-quality wiring | Electrical Engineer | 2024-10-18
7 | Sensor failure | Sensor damage or wiring issues | 2 | Pedal assist stops working, reducing ease of riding | 3 | 6 | Upgrade sensor durability and add redundancy | Design Engineer | 2024-10-30
8 | Gets muddy | Rides in mud | 1 | Becomes unpleasant to look at | 1 | 1 | Inform rider to avoid mud if they don't like it | Customer Support | 2024-10-30
9 | [5 empty] | -
10 | [5 empty] | -
11 | [5 empty] | -
12 | [5 empty] | -
13 | [5 empty] | -
14 | [5 empty] | -
15 | [5 empty] | -
16 | [5 empty] | -
17 | [5 empty] | -
18 | [5 empty] | -
19 | [5 empty] | -
20 | [5 empty] | -
21 | [5 empty] | -

## Matrix
| Risk Assessment Matrix | [6 empty] | #VALUE! |  | #VALUE!
|  |  |  | ────── Impact ──────► | [5 empty] | Risk Assessment Matrix Template
|  |  |  | Insignificant | Minor | Moderate | Major | Catastrophic |  | © 2024 Vertex42.com
|  |  |  | 1 | 2 | 3 | 4 | 5
| ─── Likelihood ──► | Almost Certain (>1 in 10) | 5 | 5 | 10 | 15 | 20 | 25 |  | Expected under most conditions. Quantitative: >95%, 1 / Week
|  | Likely (1 in 20) | 4 | 4 | 8 | 12 | 16 | 20 |  | Likely to occur often. Quantitative: >20%, 1 / Month
|  | Occasional (1 in 200) | 3 | 3 | 6 | 9 | 12 | 15 |  | Might occur occasionally. Quantitative: >1%, 1 / Year
|  | Unlikely (1 in 2000) | 2 | 2 | 4 | 6 | 8 | 10 |  | Could occur at some time. Quantitative: >0.1%, 1 / Decade
|  | Rare (<1 in 10000) | 1 | 1 | 2 | 3 | 4 | 5 |  | Very rare or highly unlikely. Quantitative: <0.01%, 1 / Century
| Matrix & Label Options | [8 empty] | TIPS
|  |  | 5 4 3 2 1: Risk Score Method; 10 8 6 4 2: Multiplication |  | Edit the Axis Rating labels as needed
|  |  | 5 4 3 2 1: Label for Vertical Axis; 10 8 6 4 2: Likelihood |  | Press Alt+Enter to create a newline within a cell
|  |  |  | Label for Horizontal Axis | Impact
|  |  |  | Include Risk Score Labels | Yes
| Color Scale Options |  | 10 8 6 4 2: Built-In
|  |  |  | Built-In |  |  | Custom Options
|  | Labels |  | Options | Color Reference | Automatic | Multiplication | Addition
|  | Very Low |  | 2 | #3D8B6D | 2 | 2 | 3
|  | Low | 15 12 9 6 3: 4; 20 16 12 8 4: 4; 25 20 15 10 5: 4
|  | Medium |  | 6 | #EDCD67 | 8 | 8 | 6
|  | High | 15 12 9 6 3: 14; 20 16 12 8 4: 14; 25 20 15 10 5: 7
|  | Extreme |  | 20 | #C23F42 | 18 | 18 | 8
|  | Catastrophic | 15 12 9 6 3: 25; 20 16 12 8 4: 25; 25 20 15 10 5: 10
Note: Colors are hard-coded into the conditional formatting conditions. Changing colors in the table above does not automatically change the color scale.
Edit the numbers in the Built-In, Multiplication, and Addition columns.
https://www.vertex42.com/ExcelTemplates/risk-assessment-matrix.html | [8 empty] | © 2024 Vertex42.com

## WhiteRed
| Risk Assessment Matrix | [6 empty] | #VALUE! |  | #VALUE!
|  |  |  | - IMPACT + | [5 empty] | Risk Assessment Matrix Template
|  |  |  | Insignificant | Minor | Moderate | Major | Catastrophic |  | © 2024 Vertex42.com
|  |  |  | 1 | 2 | 3 | 4 | 5
| ‒ LIKELIHOOD + | Almost Certain (>1 in 10) | 5 | 5 | 10 | 15 | 20 | 25
|  | Likely (1 in 20) | 4 | 4 | 8 | 12 | 16 | 20
|  | Occasional (1 in 200) | 3 | 3 | 6 | 9 | 12 | 15
|  | Unlikely (1 in 2000) | 2 | 2 | 4 | 6 | 8 | 10
|  | Rare (<1 in 10000) | 1 | 1 | 2 | 3 | 4 | 5
| Options |  | 20 16 12 8 4: Example |  | TIPS
|  |  | 5 4 3 2 1: Risk Score Method; 10 8 6 4 2: Multiplication; 20 16 12 8 4: 15 |  | Edit the Axis Rating labels as needed
|  |  | 5 4 3 2 1: Label for Vertical Axis; 10 8 6 4 2: LIKELIHOOD; 20 16 12 8 4: 22 |  | Press Alt+Enter to create a newline within a cell
|  |  |  | Label for Horizontal Axis | IMPACT |  | 11
|  |  |  | Axis Label: Arrows or ± | ± |  | 13
|  |  |  | Include Risk Score Labels | Yes |  | 24
14
|  |  |  | Color Scale Minimum Value | 2 |  | 7
|  |  |  | Color Scale Maximum Value | 20
https://www.vertex42.com/ExcelTemplates/risk-assessment-matrix.html | [8 empty] | © 2024 Vertex42.com

## BlueRed
| Risk Assessment Matrix | [6 empty] | #VALUE! |  | #VALUE!
|  |  |  | ──── IMPACT ────► | [5 empty] | Risk Assessment Matrix Template
|  |  |  | Insignificant | Minor | Moderate | Major | Catastrophic |  | © 2024 Vertex42.com
|  |  |  | 1 | 2 | 3 | 4 | 5
| ── LIKELIHOOD ──► | Almost Certain (>1 in 10) | 5 | 5 | 10 | 15 | 20 | 25
|  | Likely (1 in 20) | 4 | 4 | 8 | 12 | 16 | 20
|  | Occasional (1 in 200) | 3 | 3 | 6 | 9 | 12 | 15
|  | Unlikely (1 in 2000) | 2 | 2 | 4 | 6 | 8 | 10
|  | Rare (<1 in 10000) | 1 | 1 | 2 | 3 | 4 | 5
| Options |  | 20 16 12 8 4: Color Reference |  | TIPS
|  |  | 5 4 3 2 1: Risk Score Method; 10 8 6 4 2: Multiplication; 20 16 12 8 4: #0070C0 |  | Edit the Axis Rating labels as needed
|  |  | 5 4 3 2 1: Label for Vertical Axis; 10 8 6 4 2: LIKELIHOOD; 20 16 12 8 4: #305490 |  | Press Alt+Enter to create a newline within a cell
|  |  |  | Label for Horizontal Axis | IMPACT |  | #603860
|  |  |  | Axis Label: Arrows or ± | Arrows |  | #901C30
#C00000
|  |  |  | Color Scale Minimum Value | 2
|  |  |  | Color Scale Midpoint Value | 6
|  |  |  | Color Scale Maximum Value | 20
|  |  |  | Include Risk Score Labels | Yes
Scale for Risk Score Labels | bar: 5 4 3 2 1 to 15 12 9 6 3
|  | Labels | 5 4 3 2 1: Value; 10 8 6 4 2: Multiplication; 15 12 9 6 3: Addition
|  | Very Low | 5 4 3 2 1: 2; 10 8 6 4 2: 2; 15 12 9 6 3: 3
|  | Low | 5 4 3 2 1: 4; 10 8 6 4 2: 4; 15 12 9 6 3: 4
|  | Medium | 5 4 3 2 1: 8; 10 8 6 4 2: 8; 15 12 9 6 3: 6
|  | High | 5 4 3 2 1: 14; 10 8 6 4 2: 14; 15 12 9 6 3: 7
|  | Extreme | 5 4 3 2 1: 18; 10 8 6 4 2: 18; 15 12 9 6 3: 8
|  | Severe | 5 4 3 2 1: 25; 10 8 6 4 2: 25; 15 12 9 6 3: 10
Note: Colors are risk score labels are hard-coded into the conditional formatting conditions.
https://www.vertex42.com/ExcelTemplates/risk-assessment-matrix.html | [8 empty] | © 2024 Vertex42.com

## FMEA
DFMEA | [13 empty] | #VALUE!
Design Failure Modes and Effects Analysis | [13 empty] | Risk Assessment Matrix
Last Updated: | 2022-01-12 | [12 empty] | © 2024 Vertex42 LLC
ACTION ITEMS
Item / Function | Failure Mode | CAUSE of Failure | Frequency / Likelihood | EFFECT of Failure | Severity / Impact | Risk (F x S) | Current Controls | Detection | RPN (SxFxD) | Recommended Actions | Action Owner | Action Due Date | % Complete | Notes
Motor | Motor overheating | Overuse or poor ventilation | 2 | Motor failure, bike stops functioning | 4 | 8 | Temperature sensors and cooling fans | 6 | 48 | Improve ventilation design and use heat-resistant materials | Design Engineer | 2024-10-20 | 50% | Some Notes about this item
Battery | Battery overcharge | Faulty charging system | 2 | Battery explosion or failure | 5 | 10 | Charging circuit with overcharge protection | 3 | 30 | Implement advanced battery management system | Battery Engineer | 2024-10-15 | 100%
Braking System | Brake pad wear | Normal wear and tear | 5 | Reduced stopping ability, increased stopping distance | 4 | 20 | Routine maintenance checks | 4 | 80 | Add wear indicators on brake pads | Maintenance Team | 2024-11-01
Frame | Frame crack | Poor material quality or stress points | 2 | Structural failure, rider injury | 5 | 10 | Quality inspections during manufacturing | 5 | 50 | Use stronger, lighter materials and stress-testing | Materials Engineer | 2024-11-10 | 30%
Battery | Low battery capacity | Poor battery quality or aging | 4 | Shorter ride distance | 3 | 12 | Capacity monitoring and warning system | 4 | 48 | Improve battery quality control and user notifications | Battery Engineer | 2024-10-25
Electric Display | Display malfunction | Faulty wiring or water ingress | 3 | Loss of speed and battery status information | 2 | 6 | Waterproof casing and wiring inspections | 4 | 24 | Improve waterproofing and use higher-quality wiring | Electrical Engineer | 2024-10-18
Pedal Assist Sensor | Sensor failure | Sensor damage or wiring issues | 2 | Pedal assist stops working, reducing ease of riding | 3 | 6 | Sensor testing during assembly | 6 | 36 | Upgrade sensor durability and add redundancy | Design Engineer | 2024-10-30
Aesthetic | Gets muddy | Rides in mud | 1 | Becomes unpleasant to look at | 1 | 1 | Visually inspect | 10 | 10 | Inform rider to avoid mud if they don't like it | Customer Support | 2024-10-30
[6 empty] | - |  |  | -
[6 empty] | - |  |  | -
[6 empty] | - |  |  | -
[6 empty] | - |  |  | -
[6 empty] | - |  |  | -
[6 empty] | - |  |  | -
[6 empty] | - |  |  | -
[6 empty] | - |  |  | -
[6 empty] | - |  |  | -
[6 empty] | - |  |  | -
[6 empty] | - |  |  | -
[6 empty] | - |  |  | -
[6 empty] | - |  |  | -

## ©
Risk Assessment Template
By Vertex42.com
https://www.vertex42.com/ExcelTemplates/risk-assessment-matrix.html
© 2024 Vertex42 LLC
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery.
Please review the following license agreement to learn how you may or may not use this template. Thank you.
License Agreement
https://www.vertex42.com/licensing/EULA_privateuse.html
Do not delete this worksheet